## Sheet1
| Start | End | Months |  |  |  |  | 6 | [5 empty] | 12 | [5 empty] | 18 | [5 empty] | 24 | [5 empty] | 30 | [5 empty] | 36
1.0 Management Meetings | 1 | 36 | ✤ | ◉ | ✤ |  |  | ✤ | [5 empty] | ✤ | [5 empty] | ✤ | [5 empty] | ✤ | [5 empty] | ✤ | [5 empty] | ▼
2.0 Domains of Evidence Gathering |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
2.1 Data preparation and analysis | 1 | 30 | bar: ✤ 1 to ✤ 30
2.2 Data model design | 3 | 9 | bar: ✤ 3 to ✤ 9
2.3 Domain exploration (EU) | 4 | 9 | bar: ✤ 4 to ✤ 9
2.4 Archival data | 1 | 24 | bar: ✤ 1 to ✤ 24
2.5 Synthesis and requirements | 7 | 12 | bar: ✤ 7 to ✤ 12
3.0 Analysis Modes |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
3.1 Data acquisition (ext. sources) | 4 | 30 | bar: 4 to 30
3.2 Prestige / Centrality | 10 | 18 | bar: 10 to 18
3.3 Clustering methods | 10 | 21 | bar: 10 to 21
3.4 Correlation / significance | 10 | 24 | bar: 10 to 24
3.5 Interim data synthesis with WP4 | 16 | 18 | bar: 16 to 18
3.6 Diffusion models | 22 | 33 | bar: 22 to 33
4.0 Fieldwork Activites |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
4.1 London, UK | 3 | 24 | bar: 3 to 24
4.2 Other EU location | 7 | 24 | bar: 7 to 24
4.3 Interim data synthesis with WP3 | 16 | 18 | bar: 16 to 18
4.4 Silicon Valley | 13 | 24 | bar: 13 to 24
4.5 Co-design | 8 | 23 | bar: 8 to 11; 14 to 17; 20 to 23
4.6 Consolidate ethnographic data | 11 | 24 | bar: 11 to 12; 17 to 18; 22 to 24
5.0 Synthesis and Early Writing |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
5.1 Data synthesis | 22 | 33 | bar: 22 to ▼ 33
5.2 Network extension | 22 | 27 | bar: 22 to ▼ 27
5.3 Synthesize SNA and ethnography | 25 | 33 | bar: ▼ 25 to ▼ 33
5.4 Areas of concern/interest | 25 | 30 | bar: ▼ 25 to ▼ 30
6.0 Policy Engagement |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
6.1 Scenario design | 10 | 24 | bar: 10 to 12; 16 to 18; 22 to 24
6.2 Design challenge | 19 | 30 | bar: 19 to ✤ 30
6.3 Final scenarios specification | 25 | 36 | bar: 25 to ✤ 36
6.4 Report on scenario development | 31 | 36 | bar: ✤ 31 to ✤ 36
Research Dissemination | 1 | 36 | 2: ▼; 6: ◉; 12: ✤; 18: ✤; 24: ◉; ✤ 30: ✤; ✤ 36: ✤
|  |  | ✤ | Deliverable |  |  |  |  | ▼ | Milestone |  |  |  | ◉ | Deliverable + Milestone
This work is licensed under a Creative Commons Attribution - Non Commercial - Share Alike 4.0 International License. This work can be cited as: Howard, Philip N. (2016). Gantt Table Template for Planning Social Research - Spreadsheet. Retrieved THIS DATE from www.philhoward.org. Oxford University, Oxford, United Kingdom. pp. 1.